## Open Assignments
Assignment | Short title | Assigned Date | Due Date
Note on A1: ====== ID#AAAALSRghE0 Kevin Preston (2021-01-11 23:21:44) Use the Team assigned reference number (SPR-01, RQMT01, etc.)
Note on B1: ====== ID#AAAALSRghEY Kevin Preston (2021-01-11 23:21:44) Provide short title of the item so that the instructor does not have to go look it up.
Note on C1: ====== ID#AAAALSRghEQ Kevin Preston (2021-01-11 23:21:44) When was this assigned to you?
Note on D1: ====== ID#AAAALSRghEo Kevin Preston (2021-01-11 23:21:44) When is completion of this item due?

## Closed Assignments
Assignment | Short title | Assigned Date | Completed Date
Research | Storage/Web server research | 2025-01-17 | 2025-01-19
Research | CSV generation for import/export process research | 2025-01-19 | 2025-01-20
Practice | Prepare to give presentation of SDP | 2025-01-22 | 2025-01-26
Create RDS Server | Create and setup RDS server in AWS | 2025-02-01 | 2025-02-03
Begin Parsing Code | Write the code to parse XML files | 2025-02-08 | 2025-02-13
Export XML data to database | Help create a method to copy XML data to database | 2025-02-13 | 2025-02-20
Enable file uploads | Use file uploads and test parsing | 2025-02-20 | 2025-03-01
Add question compatibility | Add support for more types of questions and feedback after database tables are updated | 2025-03-02 | 2025-03-09
Help connect parser to frontend | Help setup the parser to the frontend | 2025-03-08 | 2025-03-14
Test Parser workflow | Ensure parser objects map well to objects in frontend | 2025-03-16 | 2025-03-20
Look into CSS for beautifying teacher view | Work on making the teacher webpage "prettier" | 2025-03-20 | 2025-03-26
Add functionlaity to parser | Teachers should be added with parser | 2025-03-26 | 2025-03-30
Make Excel Exporter | Create backend for Excel exporter | 2025-03-31 | 2025-04-06
Frontend for Database Exporter | Finish the database exporter | 2025-04-06 | 2025-04-09
Database Importer | Finish Database Importer | 2025-04-09 | 2025-04-16
Update Parser | Parser now saves with template and multiple sections | 2025-04-17 | 2025-04-20
Help find and fix bugs |  | 2025-04-20 | 2025-04-25
Note on A1: ====== ID#AAAALSRghEs Kevin Preston (2021-01-11 23:21:44) Move the Open Assignment item to this Worksheet when the item is complete. Make sure the team worksheet reflects the same status.
Note on D1: ====== ID#AAAALSRghEg Kevin Preston (2021-01-11 23:21:44) When did you complete this assignment?

## Time Sheet
Term | Class | Project | Week | Hours (Class) | Hours (Meetings) | Hours (Other) | Total for Week
Spring 2025 | CS499-03 |  | 2025-01-12 | 1 | 0.5 |  | 1.5
Spring 2025 | CS499-03 |  | 2025-01-19 | 1.5 | 4 |  | 5.5
Spring 2025 | CS499-03 |  | 2025-01-26 | 1 | 1.5 | 3 | 5.5
Spring 2025 | CS499-03 |  | 2025-02-02 | 1 | 0.8 | 3 | 4.8
Spring 2025 | CS499-03 |  | 2025-02-09 | 1 | 0.5 | 2 | 3.5
Spring 2025 | CS499-03 |  | 2025-02-16 | 2 | 0.6 | 3 | 5.6
Spring 2025 | CS499-03 |  | 2025-02-23 | 0.6 | 0.9 | 7 | 8.5
Spring 2025 | CS499-03 |  | 2025-03-02 | 2 | 0.7 | 8 | 10.7
Spring 2025 | CS499-03 |  | 2025-03-09 | 0.2 | 0.6 | 2 | 2.8
Spring 2025 | CS499-03 |  | 2025-03-16 | 0 | 0 | 6 | 6
Spring 2025 | CS499-03 |  | 2025-03-23 | 0.3 | 0.4 | 4 | 4.7
Spring 2025 | CS499-03 |  | 2025-03-30 | 2.7 | 1 | 8 | 11.7
Spring 2025 | CS499-03 |  | 2025-04-06 | 0 | 1.7 | 12 | 13.7
Spring 2025 | CS499-03 |  | 2025-04-13 | 0 | 1 | 9 | 10
Spring 2025 | CS499-03 |  | 2025-04-20 | 0 | 3.5 | 29 | 32.5
Spring 2025 | CS499-03 |  | 2025-04-27 | 0 | 4.5 | 11 | 15.5
Formulas:
Week = [Week, row above]+7
Note on C1: ====== ID#AAABZBUh_zI Kevin Preston (2024-11-20 19:49:20) Use short title from project assignment sheet. Copy to all rows.
Note on D1: ====== ID#AAAALSRghEU Kevin Preston (2021-01-11 23:21:44) Sunday Midnight is the last work date /time of the work week.
Note on E1: ====== ID#AAAALSRghEk Kevin Preston (2021-01-11 23:21:44) Time spend in class. Format is hours.fractions of hours: i.e., 1.2 is 1 hour and 12 minutes. 0.1 hour (6 minute) increments.
Note on F1: ====== ID#AAAALSRghEw Kevin Preston (2021-01-11 23:21:44) Time spend in team meetings.
Note on G1: ====== ID#AAAALSRghEc Kevin Preston (2021-01-11 23:21:44) Other hours spent working on project. Include development time, reviews, investagation and learning about tools and techniques.