## Members List
Name | Primary Role | email | Cell phone | Class01 | Class02 | Class03 | Class04 | Class05 | Work Schedule | Other Conflicts
Alex Wood | Technical Lead | anw0048@uah.edu | 443-896-7039 | MW 11:20-1:00 | MW 4:20-5:40 | TR 1:00-2:40 | TR 4:20-5:40 | Online | Unemployed | N/A
Gary Nino | Test Lead | gn0020@uah.edu | 256-337-0455 | MW 8:00-9:20 | MW 4:20-5:40 | TR 11:20-12:40 | TR 1:00-2:20 | TR 4:20-5:40 | Unemployed | N/A
Reece Milligan | Technical Writer | jrm1408@uah.edu | 901-860-3717 | MW 4:20-5:40 | T-TH 4:20-5:40 | Online | Online | Online | M-W 11 -4 T-Th 1-4 F 11 - 3 | N/A
David Fearn | Team Lead | df0051@uah.edu | 251-586-2662 | MW 8:00-9:20 | MW 4:20-5:40 | TR 11:20-1:00 | TR 4:20-5:40 |  | M/W/F 8-4 | N/A

## Meetings
Member | M01 | M02 | M03 | M04 | M05 | M06 | M07 | M08 | M09 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23
Date--> | 2025-01-08 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 2025-01-19 | 2025-01-26 | 2025-01-30 | 2025-02-01 | 2025-02-06 | 2025-02-08 | 2025-02-10 | 2025-02-12 | 2025-02-18 | 2025-02-21 | 2025-02-21 | 2025-02-28 | 2025-03-02 | 2025-03-10 | 2025-03-28 | 2025-04-02 | 2025-04-06 | 2025-04-13 | 2025-04-19 | 2025-04-23 | 2025-04-26
David Fearn | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Absent - Known | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator | Moderator
Alex Wood | Present | Present | Present | Present | Present | Present | Present | Present | Present | Moderator | Present | Present | Present | Present | Present | Present | Present | Present | Present | Absent - Known | Present | Present | Present | Absent - Known | Present
Gary Nino | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Present | Absent - Known | Present | Absent - Known
Reece Milligan | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder | Recorder
Meeting Minutes | https://docs.google.com/document/d/1-MF7TWVyrPUOFdzH864C0HmZwZ7r-veL4f9yGorAJYY/edit?usp=sharing
Software Plan | https://docs.google.com/document/d/14LupAIrKVGFsTZszSoEKuKa20keEdlMh7Hebv2eWWKo/edit?usp=sharing
Brainstorm Doc 1 | https://docs.google.com/document/d/14LupAIrKVGFsTZszSoEKuKa20keEdlMh7Hebv2eWWKo/edit?usp=sharing
Brainstorm Doc 2 | https://docs.google.com/document/d/1TJdo2sh4y-K2euzqCs9RcJP0WvdMtXYTqY2BKCW8DPA/edit?usp=sharing

## Action Items
Tracking Number | Open Date | Status | Closed Date | Assigned to | Title | Action Details | Closure Details
AI-01 |  | Closed-Resolved |  | David Fearn | Weekly Report 1 | Submit weekly report
AI-02 |  | Closed-Resolved |  | David Fearn | Weekly Report 2 | Submit weekly report
AI-03 |  | Closed-Resolved | 2025-01-26 | David Fearn | Weekly Report 3 | Submit weekly report
AI-04 | 2025-01-27 | Closed-Resolved | 2025-02-02 | David Fearn | Weekly Report 4 | Submit weekly report
AI-05 | 2025-02-02 | Closed-Resolved | 2025-02-09 | David Fearn | Weekly Report 5 | Submit weekly report
AI-06 | 2025-02-09 | Pending |  | David Fearn | Weekly Report 6 | Submit weekly report
AI-07 |  | Pending |  | David Fearn | Weekly Report 7 | Submit weekly report
AI-08 |  | Pending |  | David Fearn | Weekly Report 8 | Submit weekly report
AI-09 |  | Pending |  | David Fearn | Weekly Report 9 | Submit weekly report
AI-10 |  | Pending |  | David Fearn | Weekly Report 10 | Submit weekly report
AI-11 |  | Pending |  | David Fearn | Weekly Report 11 | Submit weekly report
AI-12 |  | Pending |  | David Fearn | Weekly Report 12 | Submit weekly report
AI-13 |  | Pending |  | David Fearn | Weekly Report 13 | Submit weekly report
AI-14 |  | Pending |  | David Fearn | Weekly Report 14 | Submit weekly report
AI-15 |  | Pending |  | David Fearn | Weekly Report 15 | Submit weekly report
AI-16 |  | Pending |  | David Fearn | Weekly Report 16 | Submit weekly report
AI-17 |  | Closed-Resolved |  | Alex Wood | Assignment Annotation | Annotate assignment details before next class
AI-18 |  | Closed-Resolved |  | Gary Nino | Assignment Annotation | Annotate assignment details before next class
AI-19 |  | Closed-Resolved |  | Reece Milligan | Assignment Annotation | Annotate assignment details before next class
AI-20 |  | Closed-Resolved |  | David Fearn | Assignment Annotation | Annotate assignment details before next class
AI-21 |  | Closed-Resolved | 2025-01-26 | Alex Wood | Begin/work on HTML website skeleton
AI-22 |  | Closed-Resolved | 2025-01-26 | Gary Nino | Investigate import/export processes
AI-23 |  | Closed-Resolved | 2025-01-26 | Reece Milligan | Flesh out database model
AI-24 |  | Closed-Resolved | 2025-01-26 | David Fearn | Investigate QTI/XML conversion
AI-25 | 2025-01-26 | Closed-Resolved | 2025-02-01 | Alex Wood | Continue work on website frontend
AI-26 | 2025-01-26 | Closed-Resolved | 2025-02-01 | Gary Nino | Practice presentation
AI-27 | 2025-01-26 | Closed-Resolved | 2025-02-01 | Reece Milligan | Investigate database implementation
AI-28 | 2025-01-26 | Closed-Resolved |  | David Fearn | Investigate exporting QTI test bank
AI-29 | 2025-02-01 | Closed-Resolved |  | David Fearn | Continue setting up AWS servers
AI-30 | 2025-02-01 | Closed-Resolved |  | Alex Wood | Continue Django setup
AI-31 | 2025-02-01 | Closed-Resolved |  | Gary Nino | Start database implementation w/ Django
AI-32 | 2025-02-01 | Closed-Resolved |  | Reece Milligan | Start database implementation w/ Django
AI-33 | 2025-02-09 | Closed-Resolved |  | David Fearn | Link RDS and EC2 servers
AI-34 | 2025-02-09 | Closed-Resolved |  | Alex Wood | Mockup website completion
AI-35 | 2025-02-09 | Closed-Resolved |  | Gary Nino | AWS RDS/EC2 support
AI-36 | 2025-02-09 | Closed-Resolved |  | Reece Milligan | Database points working locally
AI-37 | 2025-02-15 | Closed-Resolved | 2025-02-22 | David Fearn | Rework requirements
AI-38 | 2025-02-15 | Closed-Resolved | 2025-02-22 | Alex Wood | Link database witn basic backend application, continue redesign
AI-39 | 2025-02-15 | Closed-Resolved | 2025-02-22 | Gary Nino | Continue parsing QTI XML files, create sample
AI-40 | 2025-02-15 | Closed-Resolved | 2025-02-22 | Reece Milligan | Link database with basic backend application
AI-37 | 2025-02-15 | Closed-Resolved |  | David Fearn | Create parsing database import
AI-38 | 2025-02-22 | Closed-Resolved |  | Alex Wood | Finish Question page
AI-39 | 2025-02-22 | Closed-Cancelled |  | Gary Nino | Link parser to Django web app
AI-40 | 2025-02-22 | Closed-Resolved | 2025-02-10 | Reece Milligan | Connect database to Django web app
AI-41 | 2025-02-22 | Pending |  | David Fearn | Succesfully parse on AWS, connect database
AI-42 | 2025-03-01 | Closed-Resolved |  | David Fearn | Create path forward for testing
AI-43 | 2025-03-01 | Closed-Resolved |  | Alex Wood | Import QTI file into webpage
AI-44 | 2025-03-01 | Closed-Resolved |  | Gary Nino | Support Alex with parsing connection
AI-45 | 2025-03-01 | Closed-Resolved |  | Reece Milligan | Support Alex with database parsing links
AI-45 | 2025-03-08 | Closed-Resolved | 2025-03-12 | David Fearn | Link parser to Django/JS web app | Completed by Alex
AI-46 | 2025-03-08 | Closed-Resolved | 2025-03-14 | Alex Wood | Continue website implementation of test templates, improve question handling for edge case questions
AI-47 | 2025-03-08 | Closed-Resolved | 2025-03-14 | Reece Milligan | Provide support to Alex with database implementation, any other software items needed for website related to database
AI-48 | 2025-03-08 | Closed-Resolved | 2025-03-14 | Gary Nino | Provide parser support for Alex
AI-49 | 2025-03-12 | Closed-Resolved | 2025-03-15 | David Fearn | Create basic exporter functionality
AI-50 | 2025-03-16 | Closed-Resolved | 2025-03-20 | David Fearn | Link exporter functionality to web UI
AI-51 | 2025-03-16 | Closed-Negated | 2025-03-20 | Gary Nino | Test/complete full parser workflow
AI-52 | 2025-03-16 | Closed-Resolved | 2025-03-19 | Reece Milligan | Connect Django database to HTML
AI-53 | 2025-03-16 | Closed-Resolved | 2025-03-18 | Alex Wood | Complete publisher view
AI-55 | 2025-03-16 | Closed-Resolved | 2025-03-23 | David Fearn | Help draft outline for GUI presentation
AI-56 | 2025-03-16 | Closed-Resolved | 2025-03-23 | Reece Milligan | Draft outline for GUI presentation and rehearse
AI-56 | 2025-03-20 | Closed-Resolved | 2025-03-23 | David Fearn | Beautify sign-in and home pages
AI-57 | 2025-03-20 | Closed-Resolved | 2025-03-22 | Reece Milligan | Database connection and views with new API
AI-58 | 2025-03-20 | Closed-Resolved | 2025-03-27 | Gary Nino | Look into CSS for beautifying teacher view
AI-59 | 2025-03-20 | Closed-Resolved | 2025-03-22 | Alex Wood | Finalize API calls
AI-60 | 2025-03-23 | Closed-Resolved | 2025-03-26 | David Fearn | Implement CSS scrolling home page
AI-61 | 2025-03-28 | Closed-Resolved | 2025-04-05 | Reece Milligan | Support API development
AI-62 | 2025-03-28 | Closed-Resolved | 2025-04-02 | Gary Nino | Parser implementation with button
AI-63 | 2025-03-28 | Closed-Resolved | 2025-04-06 | Alex Wood | Save/load API
AI-64 | 2025-03-28 | Closed-Resolved | 2025-04-01 | David Fearn | Exporter implementation
AI-65 | 2025-03-28 | Closed-Resolved | 2025-04-01 | Alex Wood | Finish Webmaster View
AI-66 | 2025-03-28 | Closed-Resolved | 2025-04-02 | Reece Milligan | Refactor Database Models
AI-67 | 2025-03-28 | Closed-Resolved | 2025-04-05 | David Fearn | Continue work on final documentation
AI-68 | 2025-04-06 | Closed-Resolved | 2025-04-13 | Alex Wood | API saving update, deletion
AI-69 | 2025-04-06 | Closed-Resolved | 2025-04-18 | David Fearn | Test/refine Test Exporter
AI-70 | 2025-04-06 | Closed-Resolved | 2025-04-11 | Reece Milligan | Point Counter
AI-71 | 2025-04-06 | Closed-Resolved | 2025-04-10 | Gary Nino | Test/refine DB Exporter
AI-72 | 2025-04-04 | Closed-Resolved | 2025-04-05 | David Fearn | Create .gitignore
AI-73 | 2025-04-06 | Closed-Resolved | 2025-04-13 | David Fearn | Stylize signup/login pages
AI-74 | 2025-04-13 | Closed-Resolved | 2025-04-19 | Alex Wood | Refactor back end connections
AI-75 | 2025-04-13 | Closed-Resolved | 2025-04-19 | Reece Milligan | Host website on AWS
AI-76 | 2025-04-13 | Closed-Resolved | 2025-04-19 | Gary Nino | Finish .csv import
AI-77 | 2025-04-13 | Closed-Resolved | 2025-04-19 | David Fearn | Exporter tweaks/styling
AI-78 | 2025-04-19 | Closed-Resolved |  | Alex Wood | Various requirement checking and refactoring
AI-79 | 2025-04-19 | Closed-Resolved |  | Reece Milligan | Create AWS Windows instance
AI-80 | 2025-04-19 | Closed-Resolved |  | Gary Nino | Database importer and updated question saving
AI-81 | 2025-04-19 | Closed-Resolved |  | David Fearn | Presentation and requirements meeting setup, exporter page numbers w/ breaks
AI-82 | 2025-04-23 | Pending |  | David Fearn | Finalize exporter updates
AI-83 | 2025-04-23 | Pending |  | David Fearn | Create final requirements plan
AI-84 | 2025-04-23 | Pending |  | Alex Wood | Provide SME support
AI-85 | 2025-04-23 | Pending |  | Reece Milligan | Host instance of website
AI-86 | 2025-04-23 | Pending |  | Gary Nino | Add section/part naming scheme

## Epics
Epic ID | Short Title | Description | Owner
Epic01 | Administration | Submission of weekly reports, running meetings, and any other administrative actions | David Fearn
Epic02 | Recording | Recording of meeting minutes and any technical writing assignments | Reece Milligan
Epic03 | Front End Development | Create a functioning user interface/website with pages that meet all user requirements | Alex Wood
Epic04 | Back End Development | Implement the user interface defined in the front end and implement server side scripts | Gary Nino
Epic05 | Database Development | Development of model, creation of database, and other database maintenance | Reece Milligan
Epic06 | Server Hosting | Set up and maintenance of AWS servers and interfacing | David Fearn

## newStories
Parent Epic ID | User Story ID | Title | Description | Assigned to - Primary | Assigned to - Secondary | Sprint Number
Epic01 | US01 | Weekly Report 1 | Submit Team Report 1 to Canvas | David Fearn |  | 1
Epic01 | US02 | Weekly Report 2 | Submit Team Report 2 to Canvas | David Fearn |  | 2
Epic01 | US03 | Weekly Report 3 | Submit Team Report 3 to Canvas | David Fearn |  | 3
Epic01 | US04 | Weekly Report 4 | Submit Team Report 4 to Canvas | David Fearn |  | 4
Epic01 | US05 | Weekly Report 5 | Submit Team Report 5 to Canvas | David Fearn |  | 5
Epic01 | US06 | Weekly Report 6 | Submit Team Report 6 to Canvas | David Fearn |  | 6
Epic01 | US07 | Weekly Report 7 | Submit Team Report 7 to Canvas | David Fearn |  | 7
Epic01 | US08 | Weekly Report 8 | Submit Team Report 8 to Canvas | David Fearn |  | 8
Epic01 | US09 | Weekly Report 9 | Submit Team Report 9 to Canvas | David Fearn |  | 9
Epic01 | US10 | Weekly Report 10 | Submit Team Report 10 to Canvas | David Fearn |  | 10
Epic01 | US11 | Weekly Report 11 | Submit Team Report 11 to Canvas | David Fearn |  | 11
Epic01 | US12 | Weekly Report 12 | Submit Team Report 12 to Canvas | David Fearn |  | 12
Epic01 | US13 | Weekly Report 13 | Submit Team Report 13 to Canvas | David Fearn |  | 13
Epic01 | US14 | Weekly Report 14 | Submit Team Report 14 to Canvas | David Fearn |  | 14
Epic01 | US15 | Weekly Report 15 | Submit Team Report 15 to Canvas | David Fearn |  | 15
Epic01 | US16 | Weekly Report 16 | Submit Team Report 16 to Canvas | David Fearn |  | 16
Epic05 | US17 | Database Schema Design | Design a structured database schema based on project requirements | Reece Milligan |  | 3
Epic05 | US18 | Database Creation | Create a relational database with all required tables, relationships, and constraints | Reece Milligan |  | 4
Epic05 | US19 | Populate DB with test data | Insert data similar to what we will receive to begin test DB | Reece Milligan |  | 5
Epic05 | US20 | Create Stored Procedures | Develop reusable stored procedures for most common database opeations | Reece Milligan |  | 6
Epic05 | US21 | Database Backup | Establish automated backup processes to ensure data protection and availability in case of system failures or data loss | Reece Milligan |  | 7
Epic05 | US22 | Develop Database Migration Strategy | Create a safe and repeatable process for applying schema changes without losing or corrupting data. | Reece Milligan |  | 8
Epic05 | US23 | Database Performance Tuning | Continuously monitor and optimize database performance through query tuning, indexing adjustments, and resource management. | Reece Milligan |  | 9
Epic05 | US24 | Implement Database Auditing | Set up an auditing system to log and track critical database operations for monitoring and compliance purposes. | Reece Milligan |  | 10
Epic05 | US25 | Data Import and Export Functionality | Implement tools for importing and exporting data in multiple formats | David Fearn |  | 10
Epic05 | US26 | Implement Data Encryption | Encrypt sensitive data in the database to protect it from unauthorized access | Reece Milligan |  | 11
Epic05 | US27 | Data Integrity and Consistency Checks | Implement automatic checks to detect and fix data inconsistencies or errors across related database records, ensuring data reliability. | Reece Milligan |  | 12
Epic03 | US28 | Produce HTML Skeleton | Create a set of webpages connected together in a Django framework | Alex Wood |  | 3
Epic03 | US29 | Produce HTML Templates | Fill every webpage with a set of defaults representing the future design | Alex Wood |  | 4
Epic03 | US30 | Structure Templates | Increase the granularity of the defaults with CSS grid, prepare to implement functionality | Alex Wood |  | 5
Epic03 | US31 | Client Side Scripts | Add any client side functionality such as form submission and onclick events | Alex Wood |  | 6
Epic03 | US32 | Design Intuitive UI | Ensure that the design of the UI has a natural flow and is easy to navigate | Alex Wood |  | 7
Epic03 | US33 | Connect accounts to website | Hook up the user accounts from the database to the website | Alex Wood |  | 8
Epic03 | US34 | Connect database to website | Provide queries to connect users to their tests/courses/etc... | Alex Wood |  | 9
Epic03 | US35 | Visual Appeal | Design the website to be visually appealing | Alex Wood |  | 10
Epic03 | US36 | Reactive Design | Design the website to change appearance based on aspect ratio and device | Alex Wood |  | 11
Epic03 | US37 | Metadata and Debugging | Ensure metadata is accurate and complete, and code is clean and free of errors | Alex Wood |  | 12
Epic04 | US38 | Process requests to database | Use a server to connect the database to the front end of the website | Gary Nino
Epic04 | US39 | Input Validation | Ensure user inputs and file information is valid | Gary Nino
Epic04 | US40 | Error Detection and Logging | Send back correct error messages and collect logs | Gary Nino
Epic04 | US41 | Parse XML files | Extract data from XML files | Gary Nino
Epic04 | US42 | Connect database to Django | Ensure a connection between database and website | Gary Nino
Epic04 | US43 | Secure user login credentials | Ensure user login credentials are transfered and stored securely | Gary Nino
Epic04 | US44 | Create desired test file | Merge data in final export of desired HTML file | Gary Nino
Epic04 | US45 | Test Key Creation | Create appropiate answer key for selected test | Gary Nino
Epic04 | US46 | Error Prevention | Prevent user from modifying published material | Gary Nino
Epic04 | US47 | Caching Setup | Use caching to temporary store data in case of a user disconnect | Gary Nino
Epic02 | US48 | Weekly Meeting Notes 1 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US49 | Weekly Meeting Notes 2 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US50 | Weekly Meeting Notes 3 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US51 | Weekly Meeting Notes 4 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US52 | Weekly Meeting Notes 5 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US53 | Weekly Meeting Notes 6 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US54 | Weekly Meeting Notes 7 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US55 | Weekly Meeting Notes 8 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US56 | Weekly Meeting Notes 9 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US57 | Weekly Meeting Notes 10 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US58 | Weekly Meeting Notes 11 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US59 | Weekly Meeting Notes 12 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US60 | Weekly Meeting Notes 13 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US61 | Weekly Meeting Notes 14 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US62 | Weekly Meeting Notes 15 | Keep written record of discussions during the meeting | Reece Milligan
Epic02 | US63 | Weekly Meeting Notes 16 | Keep written record of discussions during the meeting | Reece Milligan
Epic06 | US64 | AWS EC2 Server Setup | Create and maintain computation server through AWS | David Fearn |  | 3
Epic06 | US65 | AWS RDS Server Setup | Create and maintain database server through AWS | David Fearn |  | 3
Epic06 | US66 | AWS S3 Server Setup | Create and storage server through AWS | David Fearn |  | 3
Epic06 | US67 | AWS Pricing Investigation | Investigate prices of individual servers and net cost of hosting | David Fearn |  | 4
Epic06 | US68 | SSL Security Certificate | Set up HTTPS for a secure web server | David Fearn |  | 7
Epic06 | US69 | Load Balancer | Create any necessary load balancing applications for multi-user traffic | David Fearn |  | 10
Epic06 | US70 | AWS Account Creation | Set up all necessary user and admin accounts for the group | David Fearn |  | 6
Epic06 | US71 | Server Installations | Install any necessary dependencies (i.e. Python3, Django, etc.) on servers | David Fearn

## newReq
Req. ID | Requirement Description | Priority | Comments | Acceptance Criteria
REQ-1 | The system shall import and export QTI-compatible files (Canvas integration). | High | Involves reading/writing QTI files, verifying structure for Canvas. | - Must successfully import a valid QTI file without error. - Must reject invalid QTI with an informative error. - Exported QTI must be accepted by Canvas (or pass QTI validation). | Data attributes – Shall track the following fields/Items:
REQ-2 | The system shall allow viewing, editing, and deleting fields associated with tests and test questions, ignoring fields not relevant for in-class tests. | High | Must only display relevant question/test fields (hide or ignore online-only attributes). | - User can open any question/test and see relevant fields (question text, correct answer, points, references, etc.). - User can edit or delete if not restricted by final test usage. - Irrelevant fields do not appear or are disabled. | Reference: Course Number, Text Reference.
REQ-3 | The system shall generate both a Test and a Test Key in HTML format (to be opened in Word). | High | Formatting must be preserved when opened in Word. | - Generated HTML for test (no answers). - Generated HTML for key (answers in red, instructions in blue). - Sufficient spacing for essays/long answers. | Data attributes – Shall track the following fields/Items:
REQ-4 | The system shall randomize questions in a section if requested and keep track of matching question answers. | Medium | Ensures each question’s correct answer remains aligned despite reordering. | - Option for randomizing question order per section. - For matching questions, the matching pairs remain correct even if items are randomized. | Question: Question type (True/False, multiple choice, matching,
REQ-5 | The system shall allow editing of test bank questions and selection of questions to create a test. | High | Basic test construction flow: pick from question bank, add to test. | - User can open a “test bank,” choose questions, and add them to a new or existing test. - Edits to question text/points are saved. | fill in the blank, short answer, essay, etc.), question, imbedded
REQ-6 | The system shall track reference information, question data attributes, cover pages, templates, attachments, and instructor feedback. | High | Ties to rubric “Data attributes,” “Cover pages,” “Attachments,” “Instructor Feedback.” | - Each question can store references (textbook, course #, time to answer, points, instructions). - Each test can have a cover page, selected template, optional attachments. - Instructor feedback is recorded (test-level, question-level). | graphics (if applicable), correct answer with imbedded graphics
REQ-7 | The system shall support a template-driven approach to test structure and formatting. | Medium | Templates define cover page, fonts, question order, bonus question placement, etc. | - User can create or edit multiple templates. - Templates define headers, footers, font size, section order. - User can choose a template when creating a new test. | (if applicable), Text reference section, default points worth,
REQ-8 | The system shall label test keys distinctly in red text on every page, with answers in red text and grading instructions in blue. | Medium | Visual formatting to distinguish final test key from test. | - “Test Key” label in red on every page. - Correct answers are in red. - Grading instructions are in blue. | estimated time (in minutes) for student to answer, tests used on,
REQ-9 | The system shall provide import/export to Excel-compatible files with a defined template. | Medium | Must have a layout for import/export (columns for question text, answers, points, references, etc.). | - Ability to export the entire database or selected questions to an Excel file. - Ability to import questions from an Excel file that follows the system’s template. | required reference material, instructions for grading question (if
REQ-10 | The system shall not allow deletion of questions used in a final test (or allow modification with a warning, creating a new question). | High | Data integrity: final tests must remain historically accurate. | - If a question is on a published final, block deletion. - If user modifies such a question, system issues a warning and can create a new version. | applicable), Instructor Comment field, and any other fields
REQ-11 | The system shall allow multi-user operation via a website with roles for Webmaster, Publisher, and Teacher. | Medium | Access control: different permissions for each role. | - Webmaster can manage site/users. - Publisher can create shared question banks. - Teacher can create personal questions/tests, provide feedback, rate publisher’s questions. | determined to be necessary by the development team.
Data attributes – Shall track the following fields/Items:
Cover pages – The first page of the test containing test
instructions, course number, test number, date of test, filename
of the test, blank for student name, grading instructions for the
key.
Data attributes – Shall track the following fields/Items:
● Templates – Allows for several templates for cover page
selection and test section order. Templates may specify font,
font size, headers, footers and tags for test name, date and
course number and blanks for recording student’s score (always
on the second page). Allow for the option of bonus questions to
be added to the template.
Data attributes – Shall track the following fields/Items:
Attachments – Reference material that is attached to the end of
the exam. For example: ARM Assembly Reference Card, Logic
Theorems, etc. Can be text and/or graphics.
Data attributes – Shall track the following fields/Items:
Instructor feedback on specific tests and test questions. Record
general information like class average on test, length of test
(time it takes most students to complete), average on specific
test question, comments on a specific test question.
CS 499 Senior Project
Project Assignment
RUBRIC
Test Creation Manager
2 ¦ Page Version 4.0
Allow the user to create new or open saved course questions. For a new
course automatically prompt for general course information: textbook
reference information (title, author, version, ISBN, website link, etc.).
Once a course is open display all the questions by type (via tabbed
pages) to the user. Allow the user to select specific textbook
section/chapter numbers or those questions used on a specified test to
display. Allow the user the ability to add, modify and delete questions
and provide instructor feedback. Warn the user if a modified or question
to be deleted has been used on a draft or final version of a test.
Allow the user to create new or open previously saved tests (draft and
final versions), cover pages and templates. A new test creation will
prompt the user to select a template or use the system default template.
Draft versions of tests may be edited and/or deleted (with verification
prompt).
Prompt the user before deleting or modifying any questions, templates,
attachments, final tests.
If the user exits the program or window without saving ask the user if
they want to exit without saving.
As the user is editing a draft test clearly displays the number of points
and bonus points the test is currently worth and estimated time to answer
the questions.
Test (Draft and Final) and Test Key generation – The test (draft
and final) and test key shall be generated in HTML format that can
be opened in Microsoft Word or similar editor. This will allow the
instructor to make final (minor) edits to the test and test key.
Spacing on the test should allow for enough white space for
student answers depending on the type of question. Essay or long
answers require more space than short answers.
CS 499 Senior Project
Project Assignment
RUBRIC
Test Creation Manager
3 ¦ Page Version 4.0
Question order in section – The user should be allowed the option
for the system to randomize the questions in a section. For
matching questions, the possible answers shall always be
randomized.
Points for questions – The system will use the default points from
the database for questions. When questions are saved the system
shall validate that the default points entered by the user. The user
should be allowed to change the points a specific question or
group of questions is worth on the draft test. For example, change
all the true/false questions to be worth 2 points or a specific essay
question to be worth 25 points.
Test Key – The test key should be clearly marked that it is the key.
This needs to be in the file name and on every page of the test in
red letters. The answers for the questions must also be in red text.
Grading instructions for the test and a question (if they exist)
should be in blue text.
Templates – Puts the test questions in an order specified by the
user. For example: True/False, Multichoice, Short answer, Essay,
attachments, etc.
Error prevention checks – Some examples: Do not allow deletion
of a question if it was ever used on a published test. Same for a
test template or a course. Warning if a question is modified after it
was used on a published test. Allow the user to save the modified
question as a new question or overwrite the existing question.
Import/Export – Provide a method to export the entire database or
selected parts of the database to an Excel compatible file. Selected
parts would be a specific course (CS121, CS214, CS309, etc.) or
specific Test for a course or selected questions. The import
capability shall be able to read an Excel compatible file
(delimited). A template must be provided so that proper formatting
of the import file can be accomplished by the user.
CS 499 Senior Project
Project Assignment
RUBRIC
Test Creation Manager
4 ¦ Page Version 4.0
Users must be able to run the program on a PC under Windows
without having to purchase additional software applications.
Website - This system shall be hosted on a multi-user website.
Roles supported by the website are:
Webmaster - Has access to the user information and is able
to manage the website.
Publisher - Can generate test questions for a specific
textbook that can be seen and copied to the teacher’s test
questions. Publishers can respond to feedback posted by
Teachers.
Teacher - Can generate test questions and share them with
other teachers. Teachers can also provide feedback to a
Publisher’s test bank or specific test questions. This can be
similar to Google or Amazon rating system (rating 1-5 and
post written feedback)

## newTest
Test Case ID | Test Case Name | Related Req. ID(s) | Preconditions | Test Steps | Expected Results
TS-1 | QTI File Management
TC-1.1 | Import Valid QTI File | REQ-1 | - System is running - User has import permissions - Valid .qti file is available | 1. Go to “Import.” 2. Select valid .qti file. 3. Click “Import.” | - Import completes with success message - Questions and metadata appear in the test bank - No errors are thrown
TC-1.2 | Import Invalid QTI File | REQ-1 | - System is running - Invalid .qti file is available | 1. Go to “Import.” 2. Select invalid .qti file. 3. Click “Import.” | - System rejects file with error (e.g., “Invalid format”) - No partial data is imported
TC-1.3 | Export QTI File | REQ-1 | - At least one completed test exists | 1. Open test 2. Click “Export” → “QTI.” 3. Download file and optionally validate with Canvas | - QTI file is successfully generated - Canvas accepts the file without error
TS-2 | Question Management
TC-2.1 | View & Edit Question Fields | REQ-2, REQ-5, REQ-6 | - A question exists in the test bank | 1. Open a question in “Edit” mode. 2. Change question text, reference, or points. 3. Save changes. | - Changes are saved - Only relevant fields (for in-class) are shown - Data attributes (points, references) update in the database
TC-2.2 | Delete Question Used in Final Test | REQ-2, REQ-10 | - Question is referenced by a final/published test | 1. Attempt to delete the question. 2. Confirm deletion if prompted. | - Deletion is blocked - System error/warning: “Cannot delete question used on final test.”
TS-3 | Test & Key Generation
TC-3.1 | Generate Draft Test in HTML | REQ-3, REQ-6, REQ-7 | - A draft test with multiple questions is created | 1. Open draft test. 2. Click “Generate Test (HTML).” 3. Open resulting file in Word. | - Draft test file in HTML is created - Questions displayed with correct formatting - Sufficient spacing for answers (especially essay questions)
TC-3.2 | Generate Final Test Key in HTML | REQ-3, REQ-8 | - A final test with correct answers & grading instructions is ready | 1. Open final test. 2. Click “Generate Key (HTML).” 3. Review the file in Word. | - File name indicates “Key.” - “Test Key” in red on every page - Answers in red, grading instructions in blue
TS-4 | Question Randomization
TC-4.1 | Randomize Question Order | REQ-4, REQ-7 | - A test section with multiple questions (including matching) | 1. Enable “Randomize” for the section. 2. Generate test preview multiple times. | - Question order changes each time - Matching answer choices also shuffle while preserving correct pairings
TS-5 | Test Lifecycle
TC-5.1 | Create New Draft Test (Selecting Questions) | REQ-5, REQ-7 | - User has a question bank - At least 5 questions available for selection | 1. Click “New Test.” 2. Prompt to select a template (or default). 3. Add questions from the bank to the draft. 4. Save test. | - Draft test is created with chosen template - Selected questions are included - User can edit or delete this draft freely
TC-5.2 | Modify Question Used on Draft Test | REQ-10 | - A question is used in a draft (not final) | 1. Edit the question text/points. 2. Save changes. | - System may warn about usage in the draft - Allows update or creation of a new question version (depending on user’s choice)
TC-5.3 | Convert Draft Test to Final | REQ-10 | - A draft test exists | 1. Open draft test. 2. Click “Publish/Finalize.” 3. Confirm finalization. | - Test is marked Final - Deletion or modifications become restricted
TC-5.4 | Prompt on Unsaved Changes | REQ-2 | - User edits a draft test or question but does not save | 1. Make changes in the editor. 2. Attempt to close or exit without saving. | - System displays “You have unsaved changes. Exit without saving?” - If “Yes,” changes are lost; if “No,” user can return and save.
TS-6 | Test Metadata
TC-6.1 | Add Attachments to a Test | REQ-6, REQ-7 | - Draft test is open | 1. Go to “Attachments” section. 2. Upload reference PDF. 3. Save test. | - Attachment is appended to the test - Appears after last question or in designated “Attachments” section (as per template)
TC-6.2 | Instructor Feedback on Test | REQ-6 | - Test is completed or existing test in the system | 1. Open test. 2. Enter general feedback (e.g., average score, time to complete). 3. Save. | - Feedback is stored under that test’s metadata - Available for future reference
TC-6.3 | Instructor Feedback on Specific Question | REQ-6 | - A question is flagged for feedback | 1. Open question in “Feedback” section. 2. Add rating/comment. 3. Save. | - Feedback is added to the question’s record - Visible to other authorized users (role-based)
TS-7 | Points Management & Test Summary
TC-7.1 | Bulk Update Points in Draft Test | REQ-5 | - Draft test with multiple T/F questions | 1. Select all T/F questions. 2. Change points from 1 to 2. 3. Save. | - All selected questions update to 2 points - Total test points reflect the change
TC-7.2 | Display Total Points & Time | REQ-6, REQ-5 | - Draft test with multiple questions (having default points/time) | 1. View the draft test “Summary.” 2. Observe total points, bonus points, estimated time. | - System displays correct cumulative points/time in real time or upon saving
TS-8 | Excel Import/Export
TC-8.1 | Export Entire Database to Excel | REQ-9 | - Large question bank with multiple courses/tests | 1. Go to “Export” → “Excel.” 2. Choose “All Data.” 3. Save the file. | - .xlsx file with all questions, courses, tests is generated - Data fields match the defined column structure
TC-8.2 | Import Questions from Excel | REQ-9 | - Excel file that matches the template is prepared | 1. Go to “Import” → “Excel.” 2. Select the file. 3. Click “Import.” | - System imports rows as new questions - Any malformed rows produce an error or warning, valid rows import successfully
TS-9 | Data Integrity & Error Prevention
TC-9.1 | Prevent Deletion of Final Test | REQ-10 | - A final/published test exists | 1. Select the final test. 2. Attempt to delete. | - System blocks deletion - Error: “Cannot delete a published final test.”
TC-9.2 | Run on Standard Windows PC | Environ. Req. | - Fresh Windows machine with no extra paid software | 1. Install the system. 2. Perform typical tasks (create test, import QTI, export Excel). | - All features run using built-in software (browser, Word if available) - No additional paid software required
TS-10 | Multi-User Roles & Permissions
TC-10.1 | Website Login & Role Permissions | REQ-11 | - Multi-user environment is set up | 1. Log in as Webmaster. 2. Verify access to site settings. 3. Log out. 4. Log in as Teacher. | - Webmaster can access user/site management - Teacher sees teacher-level features only - Publisher sees publisher-level features
TC-10.2 | Publisher Creates Shared Questions | REQ-11 | - Publisher account exists | 1. Log in as Publisher. 2. Create question in publisher’s bank 3. Log in as Teacher. 4. Copy the question to teacher’s bank. | - Teacher can see and copy publisher’s question - Publisher’s question is marked as “shared.”
TC-10.3 | Teacher Feedback & Rating System | REQ-11, REQ-6 | - Teacher logged in | 1. Find a publisher’s question. 2. Provide a rating (1-5) and comment. 3. Save feedback. | - Feedback is stored and visible to the publisher - Rating is updated or aggregated.
TC-10.4 | Webmaster Manages Website & Users | REQ-11 | - Webmaster account created | 1. Log in as Webmaster. 2. Go to “Site Administration.” 3. Create or modify user roles. | - Webmaster can manage user roles - Changes saved and enforced in the system

## Schedule
Title | Scheduled Start Date | Actual Start Date | Scheduled Complete Date | Actual Complete Date | Assigned to | Verified by
Team Report Week 1 | 2025-01-09 | 2025-01-09 | 2025-01-12 | 2025-01-12 | David Fearn | Student02
Team Report Week 2 | 2025-01-13 | 2025-01-13 | 2025-01-19 | 2025-01-19 | David Fearn | Reece Milligan
Team Report Week 3 | 2025-01-14 | 2025-01-14 | 2025-01-26 | 2025-01-25 | David Fearn | Reece Milligan
Team Report Week 4 |  | 2025-01-27 | 2025-02-02 |  | David Fearn | Reece Milligan
Team Report Week 5 |  | 2025-02-03 | 2025-02-09 |  | David Fearn | Reece Milligan
Team Report Week 6 |  | 2025-02-10 | 2025-02-16 |  | David Fearn | Reece Milligan
Team Report Week 7 |  | 2025-02-17 | 2025-02-23 | 2/23/0205 | David Fearn | Reece Milligan
Team Report Week 8 |  |  | 2025-03-02 | -619024 | David Fearn | Reece Milligan
Team Report Week 9 |  |  | 2025-03-09 | -619017 | David Fearn | Reece Milligan
Team Report Week 10 |  |  | 2025-03-16 | -619010 | David Fearn | Reece Milligan
Team Report Week 11 |  |  | 2025-03-23 | -619003 | David Fearn | Reece Milligan
Team Report Week 12 |  |  | 2025-03-30 | -618996 | David Fearn | Reece Milligan
Team Report Week 13 |  |  | 2025-04-06 | -618989 | David Fearn | Reece Milligan
Team Report Week 14 |  |  | 2025-04-13 |  | David Fearn | Reece Milligan
Team Report Week 15 |  |  | 2025-04-20 |  | David Fearn | Reece Milligan
Team Report Week 16 |  |  | 2025-04-27
Individual Report Week 1 |  |  | 2025-01-12
Individual Report Week 2 |  |  | 2025-01-19
Individual Report Week 3 |  |  | 2025-01-26
Individual Report Week 4 |  |  | 2025-02-02
Individual Report Week 5 |  |  | 2025-02-09
Individual Report Week 6 |  |  | 2025-02-16
Individual Report Week 7 |  |  | 2025-02-23
Individual Report Week 8 |  |  | 2025-03-02
Individual Report Week 9 |  |  | 2025-03-09
Individual Report Week 10 |  |  | 2025-03-16
Individual Report Week 11 |  |  | 2025-03-23
Individual Report Week 12 |  |  | 2025-03-30
Individual Report Week 13 |  |  | 2025-04-06
Individual Report Week 14 |  |  | 2025-04-13
Individual Report Week 15 |  |  | 2025-04-20
Individual Report Week 16 |  |  | 2025-04-27
SDP Submission |  |  | 2025-01-26
User Stories /Requirements |  |  | 2025-02-09
Architerctural Design |  |  | 2025-02-23
Detailed Program Review |  |  | 2025-03-02
Beta Release
Delivery Rev 1.0
Final delivery |  |  | 2024-04-28
Formulas:
Scheduled Complete Date = [Scheduled Complete Date, row above]+7
Actual Complete Date = [Actual Complete Date, row above]+7

## Key Decisions
Key Decision ID | Decision | Conclusion
KD01 | What would be the best service/server provider? | AWS
KD02 | What programming languages will we be using? | Python, MySQL, CSS3
KD03 | What should the primary backend framework use? | Python, specifically Django
KD04 | When should we start porting things to the server? | To avoid high costs, develop locally for the time being
KD05 | How should we connect the master lists with the database? | Continue work on API, save JSON solution if needed in the future
KD06
KD07
KD08
KD09
KD10
KD11
KD12

## reqTrace
Req. ID | Requirement | Test Case(s)
REQ-1 | Import/Export QTI (Canvas) | TC-1.1 TC-1.2 TC-1.3
REQ-2 | View/Edit/Delete Relevant Fields for Tests & Questions | TC-2.1 (edit fields) TC-2.2 (delete constraints) TC-5.4 (prompt on unsaved changes)
REQ-3 | Generate Test & Test Key in HTML Format | TC-3.1 (draft test) TC-3.2 (final key)
REQ-4 | Randomize Questions in a Section (matching answers remain correct) | TC-4.1
REQ-5 | Editing Test Bank Questions & Selecting to Create a Test | TC-2.1 (question edits) TC-5.1 (create new test) TC-7.1 (bulk update points)
REQ-6 | Track References, Data Attributes, Cover Pages, Templates, Attachments, Feedback | TC-2.1 (reference info) TC-6.1 (attachments) TC-6.2 TR 6.3 (feedback) TR 7.2 (time)
REQ-7 | Template-Driven Approach to Structure & Formatting | TC-2.2 (template creation) TC-5.1 (select template) TC-4.1 (randomization can be template option)
REQ-8 | Label Test Keys (answers in red, instructions in blue) | TC-3.2
REQ-9 | Import/Export to Excel | TC-8.1 TC-8.2
REQ-10 | Restrict Deletion/Modification of Questions Used in Final Test | TC-2.2 (deletion blocked) TC-5.2 (modify question) TC-9.1 (prevent final test deletion)
REQ-11 | Multi-User Website with Roles: Webmaster, Publisher, Teacher | TC-10.1 TC-10.2 TC-10.3 TC-10.4

## Risk Tracking
Risk ID | Risk Title | Likelihood | Impact Level | Risk Score | Mitigation Steps
R-01 | Loss of Member | 1 | 10 | 10 | "Next man up" approach- break down stories and epics into manageable chunks, split remaining work amongst team
R-02 | Cost of Hosting Services | 5 | 2 | 10 | Before submitting SDP, verify cost and any budgeting limitations for chosen hosting services (in particular, AWS)
R-03 | Team Member Inactivity | 2 | 5 | 10 | Host several prolonged meetings a week, as well as attempting to have a daily scrum/standup to share progress and blockers
R-04 | Busy Schedules | 3 | 3 | 9 | Be intentional with management of individual responsibilities and budget hours accordingly- plan meetings ahead of time
R-05 | Tool Interoperability Issues | 2 | 3 | 6 | Do prior investigations to make sure tools work together seamlessly and have support
R-06 | Bad key decisions | 2 | 7 | 14 | Make sure key decisions were heavily researched, ensure requirements are well-defined before programming, and regularly do testing and validating of requirements
R-07 | Transferring to Server Issues | 4 | 6 | 24 | Leave a large amount of time to be ready to deal with the server hosting and changes needed to make code functional with AWS' hosting service